| Goal #5: Develop the branding and marketing for BCCS to raise awareness and generate support for our mission. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Tasks | Responsible | Start | Resources Required | Outcomes/Measures | Comments/Improvements |
| Discovery 5.1 To position BCCS for continued success and greater growth, the committee will develop a report by September 2017 evaluating brand opportunities and challenges | Nicole Zerillo; Full Committee | 4/17 | Time of the Committee | - Convene meeting with committee members and additional committee members, where necessary - Report enrollment/retention data for each school and program, including inquiries, requested campus visits, referrals, applications, transition among schools, parent/student satisfaction surveys, as well as evaluation and screening documents - Provide data on changing demographics of students and individuals (e.g., diagnoses, behaviors, aspirations, diversity) and evolving support needs - Understand OCFS regulations regarding marketing - Complete brand environmental scan, including comparative matrix of competitors - Identify causes and organizational ambassadors - Conduct audit of existing internal and external communications channels and collateral for each school and program - Create comprehensive list of existing vendors and partner organizations that have volunteered, donated or expressed interest through our network | - First committee meeting held on Feb. 14. Those who could not attend integrated their insight into report documents; their feedback, along with this goal document, was shared with the group. |
| Development of Brand Strategy 5.2 Through April 2018, submit a report of recommendations for the sustainable development of brand communications | Nicole Zerillo; Full Committee | 12/17 | Time of the Committee | - Assess school and program brands - Review brand alignment of individual schools and programs within BCCS and within AHRC brand family - Evaluate external and internal brand perception, value drivers and satisfaction assessments (e.g. surveys, focus groups, etc.) - Plan activation of advocacy group - Recommend opportunities to deepen relationships with vendors and organizations that volunteer, donate, or express interest through our network - Propose agenda, in response to governmental and policy issues impacting organizational stakeholders - Survey community for content areas of interest - Present report of proposed tactical roll-out plan and budget to Board and senior leadership for approval |  |
| Implementation 5.3 By the end of August 2018, create and roll out updated brand utilizing storytelling components to resonate with stakeholders | Nicole Zerillo; Full Committee | 4/18 | Time of the Committee; Budget | - Clarify brand promise, attributes and key messaging for each school and program to align with the “BCCS” brand and ladder up to AHRC brand family - Adjust visual assets to match direction of brand, if needed - Test proposed brand assets with key audiences and incorporate insights into assets - Create brand identity guidelines to ensure consistency across brand vehicles and collateral (e.g., website, physical signage, business papers, online directories, advertising) - Roll out updated brand assets, alongside integrated content marketing plan to build awareness of specific schools/ programs among key audiences - Roll out brand ambassador program to respond to timely topics - Begin aggressive digital outreach ensuring that BCCS is at the top of search results |  |
| 5.3.1 On an ongoing basis, present report of recommendations to senior leadership and Board for approval | Nicole Zerillo | 4/17 | Time of the Committee | - Finalize recommendations into tactical plan - Confirm budget |  |

| Measurement 5.4 On a quarterly basis, compile measurement report sharing data on progress of newly developed brand assets | Nicole Zerillo; Full Committee | 4/17 | Time of the Committee | - Compile measurement report - Use measurement report to inform, refine or expand existing recommendations |  |
| --- | --- | --- | --- | --- | --- |