| Tasks | Committee Members | Notes |
| --- | --- | --- |
| Discovery: To position BCCS for continued success and greater growth, the committee will develop a report by September 2017 sharing data needed to make an assessment of BCCS’ brand. | Michelle Bermani; Diane Condy; Mary Gilleran |  |
| By Aug. 1, identify all locations, services and programs. | Michelle Bermani; Diane Condy; Mary Gilleran |  |
| By Aug. 1, identify enrollment/ retention metrics for each school and program, including inquiries/ requested campus visits, referrals, applications, transition among schools, and parent/student satisfaction. | Michelle Bermani; Diane Condy; Mary Gilleran |  |
| By Aug. 1, capture insight for Children’s Education Center at Brookville. | Michelle Bermani |  |
| By Aug. 1, capture insight for Marcus Avenue site. | Michelle Bermani |  |
| By Aug. 1, capture insight for Post Avenue site at Westbury. | Michelle Bermani |  |
| By Aug. 1, capture insight for SUNY Old Westbury at Westbury. | Diane Condy |  |
| By Aug. 1, capture insight for Barbara C. Wilson Preschool at Woodbury. | Diane Condy |  |
| By Aug. 1, capture insight for Children’s Residential Program | Mary Gilleran |  |
| By Aug. 1, capture insight for Home and Community Based Program | Mary Gilleran |  |
| By Aug. 3, share information and data on changing demographics of student and program participants (e.g., diagnoses, behaviors, aspirations, transition programming goals). | Christine Schulte; Zonya Mitchell |  |
| By Aug. 3, share information and data on changing support needs of employees (e.g., de-escalation techniques). | Christine Schulte; Zonya Mitchell |  |
| By Aug. 18, identify competitors and benchmark their services and brand communications vehicles (e.g., website, email, social media) beside BCCS’ assets. | Full Committee |  |
| By Aug. 18, identify how OCFS regulations impact marketing. | Mary McNamara; Michelle Bermani |  |
| By Aug. 18, gather all internal and external communications, distributions, policies and materials, including event fliers, brochures, business cards, newsletters, PA communications and content shared across social media. | Diane Condy; Mary Gilleran |  |
| By Aug. 29, conduct audit of how each school/ program currently communicates in concert and as part of the larger BCCS brand. | Mary McNamara; Marie Mamone Pickney |  |
| By Aug. 29, provide data on existing brand perception and satisfaction assessments, e.g., surveys, focus groups, etc. | Mary McNamara; Michelle Bermani; Mary Gilleran |  |
| By Sept. 7, create vendors, sponsors and donors list from the past three years. | Mary McNamara; Christine Schulte; Diane Condy |  |
| By Sept. 7, develop a list of people and organizations that have volunteered over the past three years, as well as their areas of interest. | Nicole Zerillo |  |
| By TBD, identify legislative agenda, along with governmental and policy issues impacting the organization. | Mary McNamara; Zonya Mitchell; Marie Mamone Pickney |  |
| Strategy Development (Draft; Finalized According to Data Found in Discovery Phase): Through April 18, submit a report of recommendations for sustainable development of brand communications | Nicole Zerillo; Full Committee |  |
| Evaluate reported data from Discovery Phase, with particular attention paid to brand perception and satisfaction assessments, e.g., surveys, focus groups, etc. | Nicole Zerillo; Full Committee |  |
| Brainstorm ways to improve communications mechanisms and close the gap on connecting with key audiences (e.g., content areas of interest to survey community) | Nicole Zerillo; Full Committee |  |
| Propose agenda, in response to governmental and policy issues impacting organizational stakeholders. | Mary McNamara; Christine Schulte |  |
| Identify cause and organizational ambassadors. | Mary McNamara; Christine Schulte; Diane Condy; Zonya Mitchell |  |
| Evaluate external and internal brand perception value drivers and satisfaction assessments (e.g., surveys, focus groups, etc.). | Mary McNamara; Michelle Bermani; Diane Condy |  |
| Survey community. | Mary McNamara; Michelle Bermani; Diane Condy |  |
| Clarify brand promise, attributes, key messages and drivers for each school and program. | Mary McNamara; Michelle Bermani; Diane Condy |  |
| Refine brand within existent architecture of programs and the strategy of how to communicate as a bigger BCCS brand and AHRC brand to key audiences. | Mary McNamara; Marie Mamone Pickney; Mary Gilleran |  |
| Adjust visual assets to match direction of brand. | Mary McNamara; Marie Mamone Pickney; Mary Gilleran |  |
| Test proposed brand assets with key audiences. | Mary McNamara; Zonya Mitchell; Christine Schulte |  |
| Incorporate insight from testing into brand assets. | Mary McNamara; Zonya Mitchell; Christine Schulte |  |
| Plan activation of advocacy group. | Mary McNamara, liaising with AHRC Goal #1 Committee; Christine Schulte |  |
| Present report of proposed tactical roll-out plan and budget to the Board and senior leadership for approval. | Nicole Zerillo; Full Committee |  |
| Implementation (Draft; Finalized According to Strategy Phase): By the end of August 2018, create and roll out updated brand utilizing storytelling components to connect with stakeholders including staff, families, partners and media. | Nicole Zerillo; Full Committee |  |
| Update submitted branding with Board and senior leadership recommendations. | Nicole Zerillo |  |
| Create brand identity guidelines to ensure consistency across brand vehicles and collateral (e.g., website, physical signage, business papers, online directories, advertising) | Nicole Zerillo |  |
| Continue to update and refine guidelines for staff, parents and alumni to share their contributions to the organization’s mission through newsletters, editorial schedule for blog and advocacy opportunities. | Nicole Zerillo; Mary Gilleran; Diane Condy: Michelle Bermani |  |
| Develop internal communication plan and access to collateral. | Mary McNamara; Mary Gillleran; Diane Condy; Michelle Bermani |  |
| Develop parent/staff brand ambassador program to respond to timely topics. | Mary McNamara; Marie Mamone Pickney |  |
| Begin roll out of brand, in addition to integrated content marketing plan for building brand awareness of specific programs among key audiences. | Mary McNamara |  |
| Begin aggressive digital outreach ensuring that BCCS is at the top of Search results. | Mary McNamara |  |
| Begin implementation of monitoring and measurement of marketing communications initiatives. | Mary McNamara |  |