| Goal #5: Develop the branding and communications needed for BCCS to increase awareness, support and engagement on our mission. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Chair: Nicole Zerillo Committee: Marie Mamone Pickney, Mary Gilleran, Diane Condy, Mary McNamara, Michelle Bermani, Christine Schulte, Zonya Mitchell |  |  |  |  |  |
| Tasks | Responsible | Start | Resources Required | Outcomes/Measures | Comments/Improvements |
| 5.1 Create brand consistency and awareness on staff communications materials by July 2019 | Nicole Zerillo; Full Committee | 4/17 | Time of the Committee | - Complete email signature/business disclosure footer, user-friendly upload portal and instructions, along with Policies and Procedures document - Complete business card update and finalize ready-to-go order process with printer and purchasing department - Complete digital calendar on AHRC Connect creating master calendar of key dates across schools - Complete “welcome” toolkit for new staff and families on available services and points of contact - Propose id lanyards with logo/tagline - Complete consistent signage for all schools | - Finalized design for email signature; IT began testing, coding and uploading to Outlook the signature template for AHRC’s family of organizations, including BCCS - Assembled communications contacts at each school to share ongoing updates and assist with brand consistency efforts - Quotes from signs in process, except for Westbury – Post Avenue |
| 5.2 On an ongoing basis, engage families, staff and friends on our mission and issues impacting families in our community | Nicole Zerillo; Full Committee | 12/17 | Time of the Committee | - Complete collection of all parent email addresses - Complete Family Resource Center page for families seeking insight on special needs services and tools on BCCS website - Complete Advocacy Platform page on BCCS website and trigger emails - Complete campaign highlighting BCCS mission and engaging family, friends and staff - Complete identification of programs and marketing of Family Education Series events, that can be opened to the community - Complete identification of success stories, i.e. BCCS parents and graduates who overcame challenges and share the resources and experiences that helped them be successful - Complete Staff Appreciation Day recognition - Complete campaign recognizing #DSPsRock | - A campaign with prizes and incentives is in development for September/October to engage on the organization’s mission - Scheduled to post Staff Appreciation Day images across website, social media and recruitment materials - Discussed updates of advocacy platform and outreach in Government Relations Committee - Ran online advocacy campaign on increasing tuition rates for students with disabilities and children placed in child care institutions, in tandem with New York State’s budget deadline - Exploring development of Back-to-School event, welcoming families from all schools, to break silos and broaden support network |
| 5.3 Develop promotional materials to increase awareness of BCCS community, success stories, services and professional opportunities by July 2019 | Nicole Zerillo; Full Committee | 4/18 | Time of the Committee; Budget | - Complete overview document of all services and programs - Complete Home and Community Habilitation brochure - Complete “transition” collateral and campaign for families of 13-14 year-old students on success stories after graduation | - Captured images with professional photographers to update website, social media and other collateral; begun to incorporate new pictures on website - Met with Steve Gidseg to discuss needs for collateral |
| 5.4. On an ongoing basis, ensure that the children we support, their families, staff and partners are well represented on our website, social media, media pitches and internal communications pieces | Nicole Zerillo | 4/17 | Time of the Committee | - Track the continued representation of the children we support, their families staff and partners throughout our communications channels - Evaluate outcomes and growth of social media channels - Complete streamlining of content - Completed ongoing advertising placement in New York Metro Parents online. | - FiOS1 News ran a video segment and online article on Barbara C. Wilson’s diversity initiative – the debut of their rock garden - Newsday included Barbara C. Wilson and Marcus Ave. in its #DayinthelifeLI online article; developed relationship with editor Tara Conry - Jewish Press featured Michelle Bermani’s insight in June feature article, “What You Should Know If Your Child Is Entering High School” - NECFU Credit Union connected with us via social media as they hosted #ThankaTeacher breakfast for BCCS in Brookville - Ran #ThankaTeacher online campaign - Featured Soccer Shots partners across social media - Connected with Nassau County Museum via social media on autism-friendly art classes - Currently testing content-sharing tools (e.g., Asana, Slack, Connect) to handle larger content volume; tested WuFoo for ticket system of marketing request - Connected with HR to continue implementation of monthly recruitment campaign |